## Slide 1
MANAGEMENT AND MONITORING clinical Trail system

## Slide 2: PROCEDURES
Time | Topic
1:00-1:05 | Welcome and Introductions
1:05-1:15 | What is a CTMS and Who Needs One
1:15-1:25 | Key Functions of a CTMS
1:25-1:30 | CTMS Selection Process
1:30-1:35 | System Types & Implementation Options
1:35-1:45 | Best Practices
1:45-2:00 | Q&A

## Slide 3: What is a CTMS?
Web-based technology solution that centralizes the management aspects of clinical trials
Results in streamlined business processes and reduced time and cost for most trials
Enables informed decision-making based on real-time data
Simplifies historical reporting

## Slide 4: Who needs a CTMS?
Any sponsor organization, clinical research organization, or academic medical center that:
  Manages multiple clinical trials on an
ongoing basis
  Wants to centralize and standardize the management of clinical trials and the associated business processes
  Wants to reduce study start-up time and associated costs while increasing efficiencies

## Slide 5: Key Functions of a CTMS
Investigator and Site Database
  Cataloging the history and details of all individuals and organizations associated with clinical trials
  Accelerating feasibility analyses during investigator and site selection
Study Set-Up
  Tracking essential documents
  Planning for study expenses
  Standardizing visit and payment schedules

## Slide 6: Key Functions of a CTMS (cont.)
Site Management
  Tracking of site budgets and investigator payments
  Tracking of subject
enrollment and progression
  Tracking of investigational product and ancillary supplies
  Tracking of protocol deviations and follow-up issues
  Tracking of site visits and monitoring reports

## Slide 7: Key Functions of a CTMS (cont.)
Subject Tracking
  Tracking overall subject enrollment
  Tracking individual subject visits and activities
  Tracking subject status at any time
Document Tracking
  Tracking regulatory and other documents based on a study, site, individual or company
  Tracking single documents
or document packages

## Slide 8: Key Functions of a CTMS (cont.)
Financial Tracking
  Monitoring expenses across a project
  Tracking investigator payments based on completed activities or milestones
  Tracking pass-through expenses at the site or study level
Reporting
  Monitoring trip reports
  Document tracking reports
  Payment reports

## Slide 9: Selecting a CTMS
Requirements
  Organization gathers requirements from business users, IT and other stakeholders
  Requirements are reviewed, finalized and prioritized
Demos
  Vendor RFPs are distributed and responses received
  Demos are scheduled by multiple vendors
  Gap analyses are performed
  Short list of best-fit systems is developed
Final Selection
  Following further demos, additional requirement reviews and detailed sales discussions

## Slide 10: Consideration: System Types
Standard CTMS:
  Out-of-the-box system without organization-specific customizations
  Shorter implementation time, but may not
meet all of the organization’s requirements
CTMS Accelerator:
  Pre-configured version of a standard CTMS that includes commonly-requested configurations and enhanced functionality
  Can satisfy many of the organization’s key
requirements without additional development
  Less time and cost than a customized system

## Slide 11: Consideration: System Types
Customized CTMS:
  Standard or Accelerator system that is tailored to organization specific configurations and/or enhancements
  Implementations average 9-12 months
  Costs average around $1 million, depending
on the level of customization
    Costs can be reduced by starting with an Accelerator

## Slide 12: Consideration:
Implementation Options
In-House:
  Hardware and software is owned, housed and operated by the organization and maintained by its IT department
Hosted:
  Hardware and software is housed and maintained off-site by a third party

## Slide 13: Consideration:
Hosting Options
Dedicated Hosting:
  You own the software and the servers, but the servers are housed/maintained by a data center
Shared Hosting:
  You own the software, but the servers are owned, housed, maintained by a data center and can be shared by others
Cloud Computing / SaaS:
  You lease the use of the software and
servers

## Slide 14: Best Practices:
Selection Process
Collect requirements from ALL stakeholders
Consider requirements beyond system functionality
Prioritize and define your evaluation scale
– Consider whether you need all requirements met immediately or whether some can wait for a future phase

## Slide 15: Best Practices:
Implementation Strategy
“Big Bang”
  All aspects of implementation completed simultaneously
Phased
  Implementation is broken up into chunks, such as:
Basic Installation
Point Release for Custom Configurations
Data Migration & Retirement of Legacy Systems
Integrations

## Slide 16: Best Practices:
Before Implementation
Assemble your project team
Determine the tasks, deliverables, deadlines, and responsible resources
Create a scope control plan
Design your communication plan
Begin your SOP gap analysis
Begin analyzing the organizational structure

## Slide 17: Best Practices:
During Implementation
Adhere to the Project Charter and the communication plan
Design your rollout plan
Design your training plan
Design your support plan
Involve users early and often
Create a “Data Standards” document
Mandate the use of CTMS

## Slide 18: Questions?